## Owner Summary
TEAM WORKLOAD SUMMARY (REVISED TO MATCH CODEBASE)
Team Member | Primary Phases | Key Responsibilities | # Tasks (approx.) | Status in Repo | Notes
Hardik | 1,4,5,7,8 | Project planning, backend API, integration, documentation | 14 | Implemented | Primary technical and coordination ownership
Tammana | 2,3,5,7 | Data preparation, recommendation approach, frontend modules | 12 | Implemented | Data and UI-heavy contribution areas
Taki | 2,3,5,6,8 | EDA support, model implementation support, testing and stability | 10 | Partially Implemented | Testing mostly manual in current repo
Zahidul | 5,6,7,8 | Frontend support, image handling, Docker and deployment support | 10 | Implemented | DevOps and UI support roles
All | 7,8 | Manual validation, bug fixes, final handoff | 6 | Implemented | Shared finalization tasks

## Gantt Chart
ICT CAPSTONE PROJECT - GANTT CHART (REVISED TO MATCH CODEBASE)
WBS | Task Name | Owner | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
1 | Project Initiation and Planning | Hardik | Wk 1 | Wk 2 | X | X
1.1 | Define Project Scope | Hardik | Wk 1 | Wk 1 | X
1.2 | Project Schedule and Risk Planning | Hardik | Wk 2 | Wk 2 |  | X
1.3 | Tooling Setup | Hardik | Wk 2 | Wk 2 |  | X
2 | Data Collection and Preparation | Tammana | Wk 3 | Wk 4 |  |  | X | X
2.1 | Dataset Identification | Tammana | Wk 3 | Wk 3 |  |  | X
2.2 | Data Acquisition | Hardik | Wk 3 | Wk 3 |  |  | X
2.3 | Exploratory Data Analysis | Taki | Wk 3 | Wk 3 |  |  | X
2.4 | Data Cleaning and Feature Selection | Tammana | Wk 4 | Wk 4 |  |  |  | X
2.5 | Data Documentation | Taki | Wk 4 | Wk 4 |  |  |  | X
3 | Recommendation Engine Development | Tammana and Taki | Wk 5 | Wk 6 |  |  |  |  | X | X
3.1 | Modeling Approach Finalization | Tammana | Wk 5 | Wk 5 |  |  |  |  | X
3.2 | Engine Implementation | Taki | Wk 5 | Wk 6 |  |  |  |  | X | X
3.3 | Output Formatting | Taki | Wk 6 | Wk 6 | [5 empty] | X
4 | FastAPI Backend Development | Hardik | Wk 6 | Wk 8 | [5 empty] | X | X | X
4.1 | Backend Structure | Hardik | Wk 6 | Wk 6 | [5 empty] | X
4.2 | Request/Response Schemas | Hardik | Wk 7 | Wk 7 | [6 empty] | X
4.3 | Recommendation Endpoint | Hardik | Wk 7 | Wk 8 | [6 empty] | X | X
4.4 | Error Handling Improvements | Hardik | Wk 8 | Wk 8 | [7 empty] | X
4.5 | API Documentation Check | Hardik | Wk 8 | Wk 8 | [7 empty] | X
5 | Streamlit Frontend Development | Tammana and Zahidul | Wk 8 | Wk 10 | [7 empty] | X | X | X
5.1 | Landing Page | Tammana | Wk 8 | Wk 8 | [7 empty] | X
5.2 | Automatic Recommendation Page | Tammana and Taki | Wk 9 | Wk 9 | [8 empty] | X
5.3 | Custom Recommendation Page | Zahidul | Wk 9 | Wk 9 | [8 empty] | X
5.4 | Visualization and Result Display | Tammana and Zahidul | Wk 10 | Wk 10 | [9 empty] | X
5.5 | Frontend-Backend Integration | Hardik | Wk 10 | Wk 10 | [9 empty] | X
6 | Image and UX Enhancements | Zahidul and Taki | Wk 10 | Wk 11 | [9 empty] | X | X
6.1 | Image Link Fetching | Zahidul | Wk 10 | Wk 10 | [9 empty] | X
6.2 | Fallback and Stability | Taki | Wk 11 | Wk 11 | [10 empty] | X
7 | Containerization and Deployment | Zahidul and Tammana | Wk 11 | Wk 12 | [10 empty] | X | X
7.1 | Backend Dockerfile | Zahidul | Wk 11 | Wk 11 | [10 empty] | X
7.2 | Frontend Dockerfile | Tammana | Wk 11 | Wk 11 | [10 empty] | X
7.3 | Compose Integration | Hardik | Wk 12 | Wk 12 | [11 empty] | X
7.4 | Local Deployment Verification | All | Wk 12 | Wk 12 | [11 empty] | X
8 | Validation and Documentation | All | Wk 12 | Wk 13 | [11 empty] | X | X
8.1 | Manual Functional Testing | Taki and Zahidul | Wk 12 | Wk 12 | [11 empty] | X
8.2 | Bug Fix and Refinement | All | Wk 12 | Wk 13 | [11 empty] | X | X
8.3 | Final Documentation Update | Hardik | Wk 13 | Wk 13 | [12 empty] | X

## WBS
ICT CAPSTONE PROJECT - WORK BREAKDOWN STRUCTURE (REVISED TO MATCH CODEBASE)
WBS Code | Task Name | Description | Owner | Timeline | Phase
1 | Project Initiation and Planning | Define scope, milestones, tools, risks, and communication | Hardik | Week 1-2 | Phase 1
1.1 | Define Project Scope | Clarify problem statement, goals, and deliverables | Hardik | Week 1 | Phase 1
1.2 | Project Schedule and Risk Planning | Plan timelines, owners, and risk mitigations | Hardik | Week 2 | Phase 1
1.3 | Tooling Setup | Set up GitHub, VS Code, Python env, Streamlit/FastAPI workflow | Hardik | Week 2 | Phase 1
2 | Data Collection and Preparation | Prepare Food.com recipe dataset for recommendation use | Tammana | Week 3-4 | Phase 2
2.1 | Dataset Identification | Confirm Food.com dataset as primary source | Tammana | Week 3 | Phase 2
2.2 | Data Acquisition | Store dataset in project Data folder | Hardik | Week 3 | Phase 2
2.3 | Exploratory Data Analysis | Analyze nutrition fields, ranges, and structure | Taki | Week 3 | Phase 2
2.4 | Data Cleaning and Feature Selection | Keep required columns used by recommender | Tammana | Week 4 | Phase 2
2.5 | Data Documentation | Document assumptions and external references | Taki | Week 4 | Phase 2
3 | Recommendation Engine Development | Build and validate content-based nearest-neighbor logic | Tammana and Taki | Week 5-6 | Phase 3
3.1 | Modeling Approach Finalization | Finalize content-based NN using nutrition vectors | Tammana | Week 5 | Phase 3
3.2 | Engine Implementation | Implement scaling, filtering, NN prediction pipeline | Taki | Week 5-6 | Phase 3
3.3 | Output Formatting | Transform ingredient/instruction strings to list output | Taki | Week 6 | Phase 3
4 | FastAPI Backend Development | Expose recommendation capability via API | Hardik | Week 6-8 | Phase 4
4.1 | Backend Structure | Create app entrypoint and model modules | Hardik | Week 6 | Phase 4
4.2 | Request/Response Schemas | Define Pydantic models for validation | Hardik | Week 7 | Phase 4
4.3 | Recommendation Endpoint | Implement POST /predict and health check route | Hardik | Week 7-8 | Phase 4
4.4 | Error Handling Improvements | Handle empty recommendation scenarios cleanly | Hardik | Week 8 | Phase 4
4.5 | API Documentation Check | Validate autogenerated docs in FastAPI | Hardik | Week 8 | Phase 4
5 | Streamlit Frontend Development | Build user interfaces and visual outputs | Tammana and Zahidul | Week 8-10 | Phase 5
5.1 | Landing Page | Create welcome page and app navigation | Tammana | Week 8 | Phase 5
5.2 | Automatic Recommendation Page | Build BMI/BMR flow and meal recommendation UI | Tammana and Taki | Week 9 | Phase 5
5.3 | Custom Recommendation Page | Build nutrient-input driven recommendation flow | Zahidul | Week 9 | Phase 5
5.4 | Visualization and Result Display | Render charts, recipe details, and expanders | Tammana and Zahidul | Week 10 | Phase 5
5.5 | Frontend-Backend Integration | Integrate requests from Streamlit to FastAPI | Hardik | Week 10 | Phase 5
6 | Image and UX Enhancements | Add recipe image lookup and fallback handling | Zahidul and Taki | Week 10-11 | Phase 6
6.1 | Image Link Fetching | Implement image retrieval helper | Zahidul | Week 10 | Phase 6
6.2 | Fallback and Stability | Add fallback image behavior and user-friendly output | Taki | Week 11 | Phase 6
7 | Containerization and Deployment | Package and run services with Docker Compose | Zahidul and Tammana | Week 11-12 | Phase 7
7.1 | Backend Dockerfile | Containerize FastAPI backend | Zahidul | Week 11 | Phase 7
7.2 | Frontend Dockerfile | Containerize Streamlit frontend | Tammana | Week 11 | Phase 7
7.3 | Compose Integration | Wire frontend-backend services and ports | Hardik | Week 12 | Phase 7
7.4 | Local Deployment Verification | Validate app startup and API communication | All | Week 12 | Phase 7
8 | Validation and Documentation | Run manual checks and finalize docs | All | Week 12-13 | Phase 8
8.1 | Manual Functional Testing | Check both recommendation flows end-to-end | Taki and Zahidul | Week 12 | Phase 8
8.2 | Bug Fix and Refinement | Resolve observed issues | All | Week 12-13 | Phase 8
8.3 | Final Documentation Update | Update README and project summary artifacts | Hardik | Week 13 | Phase 8