## WBS
ICT CAPSTONE PROJECT — WORK BREAKDOWN STRUCTURE (WBS)
WBS Code | Task Name | Description | Owner | Timeline | Phase
1 | ▶ Project Initiation & Planning | Establish project foundation, scope, and tooling | Hardik | Week 1–2 | Phase 1
1.1 | • Define Project Scope | Clarify objectives, constraints, and success criteria | Hardik | Week 1 | Phase 1
1.2 | • Identify Stakeholders | Identify tutor, team members, and end users | Hardik | Week 2 | Phase 1
1.3 | • Project Schedule Planning | Map phases to weeks and assessment deliverables | Hardik | Week 2 | Phase 1
1.4 | • Project Tooling Setup | Git, GitHub, VS Code, Zoom, Google Sheets, Streamlit, FastAPI, Docker | Hardik | Week 2 | Phase 1
1.5 | • Risk Register Initialisation | Document initial project risks, likelihood, impact, and mitigation | Hardik | Week 2 | Phase 1
2 | ▶ Data Collection & Preparation | Source, explore, clean, and document all datasets | Tammana | Week 3–4 | Phase 2
2.1 | • Dataset Identification | Select www.Food.com and OpenNutrition.com datasets | Tammana | Week 3 | Phase 2
2.2 | • Data Acquisition | Download and store raw datasets in repo structure | Hardik | Week 3 | Phase 2
2.3 | • Dataset Exploration (EDA) | Basic EDA: missing values, distributions, outliers | Taki | Week 3 | Phase 2
2.4 | • Data Cleaning | Handle missing values, duplicates, inconsistent units | Tammana | Week 4 | Phase 2
2.5 | • Feature Engineering | Derive nutrient features, diet tags, cuisine types, etc. | Tammana | Week 4 | Phase 2
2.6 | • Data Documentation | Document data sources, preprocessing steps, assumptions | Taki | Week 4 | Phase 2
2.7 | • Data Version Control | Commit cleaned datasets and EDA notebooks to GitHub | Hardik | Week 4 | Phase 2
3 | ▶ Database Setup & Design | Design, implement, and validate the project database | Hardik & Tammana | Week 4–5 | Phase 3
3.1 | • Data Storage Requirements | Decide what needs to be stored (users, preferences, recipes, logs) | Hardik | Week 4 | Phase 3
3.2 | • Conceptual Data Model (ERD) | ERD: entities and relationships (User, Recipe, Nutrient, Preference, History) | Hardik | Week 4 | Phase 3
3.3 | • Logical & Physical Schema Design | Tables, keys, indexes (PostgreSQL / SQLite) | Hardik | Week 5 | Phase 3
3.4 | • Database Implementation | Create DB, schemas, and initial tables | Hardik | Week 5 | Phase 3
3.5 | • Data Loading & Ingestion | Load cleaned data into database | Zahidul | Week 5 | Phase 3
3.6 | • Database Testing & Validation | Test queries, performance, and integrity constraints | Taki | Week 5 | Phase 3
3.7 | • Database Documentation | Document schema, relationships, and query patterns | Hardik | Week 5 | Phase 3
4 | ▶ Core Application Development | Build backend logic, APIs, and recommendation engine | Hardik & Tammana | Week 6–9 | Phase 4
4.1 | • Backend Architecture Design | Define modules, layers, and API structure | Hardik, Tammana & Taki | Week 6 | Phase 4
4.2 | • User Management Module | Registration, login (JWT/session), profile model | Taki & Zahidul | Week 7 | Phase 4
4.3 | • Recommendation Engine Design | Choose approach (rule-based, content-based, or simple ML) | Tammana | Week 7 | Phase 4
4.4 | • Recommendation Engine Implementation | Implement logic using processed data and user inputs | Taki & Zahidul | Week 8 | Phase 4
4.5 | • API Endpoint Implementation | Endpoints: user profile, preferences, recommendations, history | Hardik | Week 8 | Phase 4
4.6 | • Error Handling & Logging | Standardised responses and logging for debugging | Hardik | Week 8 | Phase 4
4.7 | • Backend Unit Testing | Tests for core functions and all endpoints | Taki | Week 9 | Phase 4
4.8 | • API Documentation (Swagger/OpenAPI) | Auto-generate and review API docs via FastAPI | Hardik | Week 9 | Phase 4
5 | ▶ User Interface Development | Design and build the Streamlit frontend | Tammana & Zahidul | Week 9–11 | Phase 5
5.1 | • UI/UX Design | Define layout, navigation, colour scheme, user flow | Tammana & Zahidul | Week 9 | Phase 5
5.2 | • Streamlit Page Structure | Home, profile setup, diet preferences, recommendations page | Tammana, Taki & Zahidul | Week 9 | Phase 5
5.3 | • Forms & Input Handling | Collect age, gender, goals, dietary restrictions, activity level | Hardik & Taki | Week 10 | Phase 5
5.4 | • Display of Recommendations | Show meals, nutrients, and explanations | Hardik & Tammana | Week 10 | Phase 5
5.5 | • Backend API Integration | Connect Streamlit to FastAPI endpoints | Hardik | Week 10 | Phase 5
5.6 | • Frontend Validations & UX Tweaks | Improve clarity, error messages, loading states | Zahidul & Taki | Week 11 | Phase 5
5.7 | • Frontend Testing | Functional testing of all user flows | Tammana, Zahidul & Taki | Week 11 | Phase 5
5.8 | • Accessibility & Responsiveness Check | Ensure UI is usable across screen sizes and browsers | Zahidul | Week 11 | Phase 5
6 | ▶ Testing & Deployment | End-to-end testing, containerisation, and deployment | Hardik | Week 12–13 | Phase 6
6.1 | • Test Plan Creation | Define test cases: functional, integration, basic performance | Hardik | Week 12 | Phase 6
6.2 | • Integration Testing | End-to-end tests: UI → API → DB → response | Taki | Week 12 | Phase 6
6.3 | • Bug Fixing & Refinement | Prioritise and resolve all identified issues | ALL | Week 12 | Phase 6
6.4 | • Dockerisation | Dockerfile for backend & frontend; Docker Compose for both | Zahidul & Tammana | Week 12 | Phase 6
6.5 | • CI/CD Setup (GitHub Actions) | Build, test, and optionally deploy on push/PR | Hardik | Week 12 | Phase 6
6.6 | • Final Deployment | Run via Docker locally for demo; optional cloud deployment | ALL | Week 12 | Phase 6
6.7 | • Deployment Verification | Confirm app runs cleanly on all team laptops | ALL | Week 13 | Phase 6
6.8 | • Performance & Load Testing | Basic load test on recommendation endpoints | Taki | Week 13 | Phase 6
7 | ▶ Project Management & Collaboration | Ongoing coordination, tracking, and risk management | ALL | All Weeks | Phase 7
7.1 | • Weekly Zoom Meetings | Agenda, discussion, decisions, and action items | ALL | All Weeks | Phase 7
7.2 | • Weekly Minutes of Meeting | Hardik documents and submits ~200 words per week | ALL | All Weeks | Phase 7
7.3 | • Task Tracking & Assignment | Use GitHub Projects board for tasks and progress | ALL | All Weeks | Phase 7
7.4 | • Risk & Issue Tracking | Identify risks (time, bugs, integration) and mitigation strategies | ALL | All Weeks | Phase 7
7.5 | • Team Communication Standards | Agree on response times, channels, and escalation paths | ALL | Week 1 | Phase 7
8 | ▶ Assessment Deliverables | All academic submission requirements across the semester | ALL | All Weeks | Phase 8
8.1 | ◆ Weekly Individual Reflective Essays | 200 words + evidence (screenshots, commits, code snippets) | ALL | Weeks 1–12 | Phase 8
8.1.1 | • Weekly Reflection – Week 1 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 1 | Phase 8
8.1.2 | • Weekly Reflection – Week 2 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 2 | Phase 8
8.1.3 | • Weekly Reflection – Week 3 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 3 | Phase 8
8.1.4 | • Weekly Reflection – Week 4 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 4 | Phase 8
8.1.5 | • Weekly Reflection – Week 5 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 5 | Phase 8
8.1.6 | • Weekly Reflection – Week 6 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 6 | Phase 8
8.1.7 | • Weekly Reflection – Week 7 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 7 | Phase 8
8.1.8 | • Weekly Reflection – Week 8 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 8 | Phase 8
8.1.9 | • Weekly Reflection – Week 9 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 9 | Phase 8
8.1.10 | • Weekly Reflection – Week 10 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 10 | Phase 8
8.1.11 | • Weekly Reflection – Week 11 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 11 | Phase 8
8.1.12 | • Weekly Reflection – Week 12 | Individual essay: 200+ words with evidence (screenshots, commits, code snippets) | ALL | Week 12 | Phase 8
8.2 | ◆ Weekly Group Minutes Submissions | Hardik submits group minutes based on Zoom + progress | ALL | Weeks 1–12 | Phase 8
8.2.1 | • Minutes Submission – Week 1 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 1 | Phase 8
8.2.2 | • Minutes Submission – Week 2 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 2 | Phase 8
8.2.3 | • Minutes Submission – Week 3 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 3 | Phase 8
8.2.4 | • Minutes Submission – Week 4 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 4 | Phase 8
8.2.5 | • Minutes Submission – Week 5 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 5 | Phase 8
8.2.6 | • Minutes Submission – Week 6 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 6 | Phase 8
8.2.7 | • Minutes Submission – Week 7 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 7 | Phase 8
8.2.8 | • Minutes Submission – Week 8 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 8 | Phase 8
8.2.9 | • Minutes Submission – Week 9 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 9 | Phase 8
8.2.10 | • Minutes Submission – Week 10 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 10 | Phase 8
8.2.11 | • Minutes Submission – Week 11 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 11 | Phase 8
8.2.12 | • Minutes Submission – Week 12 | Hardik submits; content based on Zoom meeting and weekly progress | ALL | Week 12 | Phase 8
8.3 | ◆ Group Project Proposal | Mid-semester formal proposal document | ALL | Mid-Semester | Phase 8
8.3.1 | • Problem Definition & Motivation | State the problem, why it matters, and project goals | ALL | Mid-Semester | Phase 8
8.3.2 | • Literature Review & Related Work | Review existing food/diet recommendation systems | ALL | Mid-Semester | Phase 8
8.3.3 | • System Scope & Objectives | Define boundaries, features in/out of scope | ALL | Mid-Semester | Phase 8
8.3.4 | • High-Level Architecture & Technologies | System diagram and tech stack justification | ALL | Mid-Semester | Phase 8
8.3.5 | • WBS & Gantt Chart | Complete WBS with Gantt chart timeline | ALL | Mid-Semester | Phase 8
8.3.6 | • Methodology & Plan for Remaining Work | Development methodology and sprint plan | ALL | Mid-Semester | Phase 8
8.3.7 | • References & Citations | APA/IEEE formatted references | ALL | Mid-Semester | Phase 8
8.4 | ◆ Final Group Project Document | End-of-semester comprehensive technical report | ALL | Week 13 | Phase 8
8.4.1 | • Introduction & Background | Context, motivation, and project overview | ALL | Week 13 | Phase 8
8.4.2 | • Detailed System Design | High-level and low-level system design | ALL | Week 13 | Phase 8
8.4.3 | • Implementation Details | Backend, frontend, DB, Docker, CI/CD details | ALL | Week 13 | Phase 8
8.4.4 | • Testing Strategy & Results | Test plans, results, and coverage | ALL | Week 13 | Phase 8
8.4.5 | • Discussion, Limitations & Future Work | Critical analysis and improvement recommendations | ALL | Week 13 | Phase 8
8.4.6 | • Conclusion | Summary of achievements and outcomes | ALL | Week 13 | Phase 8
8.4.7 | • References & Appendix | All references and supplementary material | ALL | Week 13 | Phase 8
8.5 | ◆ Presentation & Demo | Final project presentation and live demonstration | ALL | Week 13 | Phase 8
8.5.1 | • Slide Deck Structure (16 Slides) | Title, problem, objectives, datasets, architecture, design, implementation, demo, testing, results, future work, Q&A | ALL | Week 13 | Phase 8
8.5.2 | • Live Demo Preparation | Stable build, tested flows, backup plan | ALL | Week 13 | Phase 8
8.5.3 | • Rehearsals | Assign speakers, practice timing and Q&A | ALL | Week 13 | Phase 8
8.5.4 | • Final Presentation Delivery | All the best to all of us! | ALL | Week 13 | Phase 8
LEGEND
Phase 1 | Project Initiation & Planning
Phase 2 | Data Collection & Preparation
Phase 3 | Database Setup & Design
Phase 4 | Core Application Development
Phase 5 | User Interface Development
Phase 6 | Testing & Deployment
Phase 7 | Project Management
Phase 8 | Assessment Deliverables

## Gantt Chart
ICT CAPSTONE PROJECT — GANTT CHART (13-WEEK SCHEDULE)
WBS | Task Name | Owner | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
1 | ▶ Project Initiation & Planning | Hardik | Wk 1 | Wk 2 | █ | █
1.1 | • Define Project Scope | Hardik | Wk 1 | Wk 1
1.2 | • Identify Stakeholders | Hardik | Wk 2 | Wk 2
1.3 | • Project Schedule Planning | Hardik | Wk 2 | Wk 2
1.4 | • Project Tooling Setup | Hardik | Wk 2 | Wk 2
1.5 | • Risk Register Initialisation | Hardik | Wk 2 | Wk 2
2 | ▶ Data Collection & Preparation | Tammana | Wk 3 | Wk 4 |  |  | █ | █
2.1 | • Dataset Identification | Tammana | Wk 3 | Wk 3
2.2 | • Data Acquisition | Hardik | Wk 3 | Wk 3
2.3 | • Dataset Exploration (EDA) | Taki | Wk 3 | Wk 3
2.4 | • Data Cleaning | Tammana | Wk 4 | Wk 4
2.5 | • Feature Engineering | Tammana | Wk 4 | Wk 4
2.6 | • Data Documentation | Taki | Wk 4 | Wk 4
2.7 | • Data Version Control | Hardik | Wk 4 | Wk 4
3 | ▶ Database Setup & Design | Hardik & Tammana | Wk 4 | Wk 5 |  |  |  |  | █
3.1 | • Data Storage Requirements | Hardik | Wk 4 | Wk 4
3.2 | • Conceptual Data Model (ERD) | Hardik | Wk 4 | Wk 4
3.3 | • Logical & Physical Schema Design | Hardik | Wk 5 | Wk 5
3.4 | • Database Implementation | Hardik | Wk 5 | Wk 5
3.5 | • Data Loading & Ingestion | Zahidul | Wk 5 | Wk 5
3.6 | • Database Testing & Validation | Taki | Wk 5 | Wk 5
3.7 | • Database Documentation | Hardik | Wk 5 | Wk 5
4 | ▶ Core Application Development | Hardik & Tammana | Wk 6 | Wk 9 | [5 empty] | █ | █ | █ | █
4.1 | • Backend Architecture Design | Hardik, Tammana & Taki | Wk 6 | Wk 6
4.1.1 | Backend Architecture Planning | Hardik | Wk 6 | Wk 6
4.1.2 | Database Structure Design | Tammana | Wk 6 | Wk 6
4.1.3 | Architecture Review | Taki | Wk 6 | Wk 6
4.2 | • User Management Module | Taki & Zahidul | Wk 7 | Wk 7
4.1.1 | User Authentication Logic | Taki | Wk 7 | Wk 7
4.1.2 | User Database Integration | Zahidul | Wk 7 | Wk 7
4.3 | • Recommendation Engine Design | Tammana & Taki | Wk 7 | Wk 7
4.3.1 | Recommendation Algorithm Research | Tammana | Wk 7 | Wk 7
4.3.2 | Model Design Documentation | Taki | Wk 7 | Wk 7
4.4 | • Recommendation Engine Implementation | Taki & Zahidul | Wk 8 | Wk 8
4.4.1 | Recommendation Algorithm Coding | Taki | Wk 8 | Wk 8
4.4.2 | Backend Model Integration | Zahidul | Wk 8 | Wk 8
4.5 | • API Endpoint Implementation | Hardik & Tammana | Wk 8 | Wk 8
4.5.1 | API Route Development | Hardik | Wk 8 | Wk 8
4.5.2 | API Request & Response Handling | Tammana | Wk 8 | Wk 8
4.6 | • Error Handling & Logging | Hardik & Zahidul | Wk 8 | Wk 8
4.6.1 | Error Handling Implementation | Hardik | Wk 8 | Wk 8
4.6.2 | Logging Mechanism Setup | Zahidul | Wk 8 | Wk 8
4.7 | • Backend Unit Testing | Taki & Zahidul | Wk 9 | Wk 9
4.7.1 | Unit Test Case Development | Taki | Wk 9 | Wk 9
4.7.2 | Backend Testing Execution | Zahidul | Wk 9 | Wk 9
4.8 | • API Documentation (Swagger/OpenAPI) | Hardik & Taki | Wk 9 | Wk 9
4.8.1 | API Endpoint Documentation | Hardik | Wk 9 | Wk 9
4.8.2 | API Usage Examples Documentation | Taki | Wk 9 | Wk 9
5 | ▶ User Interface Development | Tammana & Zahidul | Wk 9 | Wk 11 | [8 empty] | █ | █ | █
5.1 | • UI/UX Design | Tammana & Zahidul | Wk 9 | Wk 9
5.1.1 | Wireframe Design | Tammana | Wk 9 | Wk 9
5.1.2 | Interface Layout Development | Zahidul | Wk 9 | Wk 9
5.2 | • Streamlit Page Structure | Tammana & Zahidul | Wk 9 | Wk 9
5.2.1 | Homepage Layout Setup | Tammana | Wk 9 | Wk 9
5.2.2 | Page Navigation Setup | Zahhidul | Wk 9 | Wk 9
5.3 | • Forms & Input Handling | Hardik & Taki | Wk 10 | Wk 10
5.3.1 | Input Form Design | Hardik | Wk 10 | Wk 10
5.3.2 | Input Validation Logic | Taki | Wk 10 | Wk 10
5.4 | • Display of Recommendations | Hardik & Tammana | Wk 10 | Wk 10
5.4.1 | Recommendation Result UI | Hardik | Wk 10 | Wk 10
5.4.2 | Recommendation Formatting & Display | Tammana | Wk 10 | Wk 10
5.5 | • Backend API Integration | Hardik | Wk 10 | Wk 10
5.5.1 | Connect Frontend to Backend API | Hardik | Wk 10 | Wk 10
5.5.2 | API Data Handling in UI | Hardik | Wk 10 | Wk 10
5.6 | • Frontend Validations & UX Tweaks | Zahidul & Taki | Wk 11 | Wk 11
5.6.1 | Form Validation Implementation | Zahidul | Wk 11 | Wk 11
5.6.2 | UI Improvements & UX Refinement | Taki | Wk 11 | Wk 11
5.7 | • Frontend Testing | Tammana & Zahidul | Wk 11 | Wk 11
5.7.1 | Functional UI Testing | Tammana | Wk 11 | Wk 11
5.7.2 | UI Bug Fixing | Zahidul | Wk 11 | Wk 11
5.8 | • Accessibility & Responsiveness Check | Zahidul | Wk 11 | Wk 11
6 | ▶ Testing & Deployment | Hardik | Wk 12 | Wk 13 | [11 empty] | █ | █
6.1 | • Test Plan Creation | Hardik | Wk 12 | Wk 12
6.2 | • Integration Testing | Taki | Wk 12 | Wk 12
6.3 | • Bug Fixing & Refinement | ALL | Wk 12 | Wk 12
6.4 | • Dockerisation | Zahidul & Tammana | Wk 12 | Wk 12
6.5 | • CI/CD Setup (GitHub Actions) | Hardik | Wk 12 | Wk 12
6.6 | • Final Deployment | ALL | Wk 12 | Wk 12
6.7 | • Deployment Verification | ALL | Wk 13 | Wk 13
6.8 | • Performance & Load Testing | Taki | Wk 13 | Wk 13
7 | ▶ Project Management & Collaboration | ALL | Wk 1 | Wk 13 | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
7.1 | • Weekly Zoom Meetings | ALL | Wk 1 | Wk 13
7.2 | • Weekly Minutes of Meeting | ALL | Wk 1 | Wk 13
7.3 | • Task Tracking & Assignment | ALL | Wk 1 | Wk 13
7.4 | • Risk & Issue Tracking | ALL | Wk 1 | Wk 13
7.5 | • Team Communication Standards | ALL | Wk 1 | Wk 1
8 | ▶ Assessment Deliverables | ALL | Wk 1 | Wk 13 | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
8.1 | • Weekly Individual Reflective Essays | ALL | Wk 1 | Wk 12
8.2 | • Weekly Group Minutes Submissions | ALL | Wk 1 | Wk 12
8.3 | • Group Project Proposal | ALL | Wk 1 | Wk 13
8.4 | • Final Group Project Document | ALL | Wk 13 | Wk 13
8.5 | • Presentation & Demo | ALL | Wk 13 | Wk 13
Milestones | Key project milestones |  |  |  |  | ◆Plan |  |  | ◆DB |  |  |  | ◆Dev |  | ◆UI |  | ◆Done
LEGEND
Phase 1 – Project Initiation
Phase 2 – Data Collection
Phase 3 – Database
Phase 4 – Core Development
Phase 5 – UI Development
Phase 6 – Testing & Deployment
Phase 7 – Project Management
Phase 8 – Assessments
◆ | Milestone

## Owner Summary
TEAM WORKLOAD SUMMARY
Team Member | Colour Code | Primary Phases | Key Responsibilities | # Tasks (excl. ALL) | Notes
Hardik | ■ See colour | 1, 3, 4, 6 | Project lead, DB design, Backend APIs, CI/CD, Dockerisation, Minutes | 18 | Primary technical lead & PM
Tammana | ■ See colour | 2, 4, 5 | Data collection & cleaning, Feature engineering, Recommendation engine design, UI | 12 | Data & ML lead
Taki | ■ See colour | 2, 3, 4, 5, 6 | EDA, DB testing, Backend architecture, User management, Integration testing | 11 | Full-stack support
Zahidul | ■ See colour | 3, 4, 5, 6 | Data ingestion, User management, Recommendation engine, UI, Dockerisation | 9 | Backend & DevOps support
ALL (Team) | ■ See colour | 7, 8 | Weekly meetings, minutes, reflections, assessments, bug fixing, deployment | 30 | Shared responsibilities